## Slide 1: Network Diagrams and Activity on Node Analysis (AON)
MGMT-3105 Lecture 6
http://worldartsme.com/images/decisionmaking-clipart-1.jpg

## Slide 2: Project Time Management
Project Time Management includes all the process that are needed to manage the timely completion of the project.
  Plan Schedule Management
  Define Activities
  Sequence the activities
  Estimate activity resources
  Estimate activity durations
  Develop schedule
  Control schedule.
Today we are covering only the processes in bold Red

## Slide 3: Define Activities Process
First you need to generate the Work Breakdown Structure (WBS) for the project as demonstrated. This is done by identifying all the activities that need to be completed to meet the project deliverables.
From the WBS, you need to generate the Network Activity Diagram for the project – commonly referred to as the Network Diagram.

## Slide 4: WBS Review What is the definition of WBS?
A work breakdown structure (WBS) is a deliverable
oriented grouping of project components that organizes
and defines the total scope of the project.
The WBS is the project scope broken down into smaller manageable pieces or tasks. If all the tasks are completed, then the sum of those tasks will equal the project scope.
Level 1 of a WBS is the scope broken down in broad categories.
Level 2 is each of these broad categories broken down into smaller more manageable tasks or smaller categories (work packages). These tasks take between 8 and 80 hours to complete for the average project. You do not want to break tasks down below 8 hours as it becomes micromanaging at that point. Tasks more than 80 hours are too broad to manage properly.

## Slide 5
Sample WBS for Project Management |  |  |  |  |  |  |  | 
1 | Fabrication and Assembly of components for tool rest (Project 275) |  |  |  |  |  |  | 
(Level 1) | 1 | Material |  |  |  |  |  | 
 |  | 1.1 | Material lists prepared from drawings |  |  |  |  | 
(Level 2) |  | 1.3 | Material Ordered |  |  |  |  | 
 |  | 1.5 | Material inspected upon delivery |  |  |  |  | 
 |  | 1.7 | Prepare material for fabrication |  |  |  |  | 
(Level 3) |  |  | 1.7.1 | Stock squared for base plates |  |  |  | 
 |  |  | 1.7.3 | Round stock sized for turning |  |  |  | 
 | 3 | Equipment |  |  |  |  |  | 
 |  | 3.1 | CNC 1 and 2 booked for required fabrication time |  |  |  |  | 
 |  | 3.3 | Lathes 1, 2 and 3 booked for required fabrication time |  |  |  |  | 
 | 5 | Manpower |  |  |  |  |  | 
 |  | 5.1 | Manpower availability with Fabrication Manager determined |  |  |  |  | 
 |  |  | 5.1.1 |  |  |  |  | 
 |  | 5.3 | Manpower availability with Assembly Manager determined |  |  |  |  | 
 |  |  | 5.3.1 | Created / Posted schedule for assembly operators |  |  |  | 
 |  | 5.5 | Manpower availability with Quality Manager determined |  |  |  |  | 
 |  |  | 5.5.1 | Created / Posted schedule for Quality technician |  |  |  | 
 | 7 | Fabrication |  |  |  |  |  | 
 | 9 | Quality Inspections |  |  |  |  |  | 
 | 11 | Assembly |  |  |  |  |  | 
 | 13 | Quality Inspections |  |  |  |  |  | 
 | 15 | Customer Inspection |  |  |  |  |  | 
 | 17 | Packaging |  |  |  |  |  | 
 | 19 | Shipping |  |  |  |  |  | 
Create / Post schedule for Fabrication operators

## Slide 6: WBS Example

## Slide 7: The Rules for creating Network Activity Diagrams
Some determination of activity precedence ordering must be done prior to creating the network.
Network diagrams usually flow from left to right.
An activity cannot begin until all preceding connected activities have been completed.
Arrows on networks indicate precedence and logical flow. Arrows can cross over each other, although it is helpful for clarity’s sake to limit this effect when possible.
Each activity should have a unique identifier associated with it (number, letter, code, etc.).
Looping, or recycling through activities, is not permitted.
Although not required, it is common to start a project from a single beginning node.
A single node point also is typically used as a project end indicator.

## Slide 8: Key Scheduling Terminology - simplified
Activity:
Scope: The work content and products of a project.
Work Breakdown Structure (WBS): A task-oriented grouping of activities that organizes, defines, and graphically displays the total work to be accomplished in order to achieve the final objectives (deliverables) of the project.
Work Package: A deliverable at the lowest level of the work breakdown structure.
Project Network Diagram: Any schematic display of the logical relationships of project activities.
Path: A sequence of activities defined by the project network logic.
Early Start Date (ES): The earliest possible date on which the uncompleted portions of an activity can be started.
Late Start Date (LS): The latest possible date that an activity may begin without delaying a specified milestone.

## Slide 9: Key Scheduling Terminology – simplified (cont.)
Early Finish
Late Finish
Forward Pass – Network calculations that determine the earliest start/finish time for each activity.
Backward Pass – Calculation of late start and late finish times for all uncompleted network activities.
Event – A point in time when an activity is either started or completed.
Node – One or more defining points of a network.
Predecessors – Those activities that must be completed prior to an activity in the network.
Successors – Activities that cannot be started until previous activities have been completed.
Merge Activity – An activity with 2 or more immediate predecessor activities flowing into it.

## Slide 10: Key Scheduling Terminology – simplified (cont.)
Burst Activity: An activity with 2 or more immediate successor activities flowing out from it.
Float (Slack): The amount of time an activity may be delayed from its early start without delaying the finish of the project.
Critical Path: The path through the project network with the longest duration.
Critical Path Method: A network analysis technique used to determine which sequence of activities (which path) has the least amount of scheduling flexibility and therefore will most likely determine when the project can be completed.

## Slide 11: Key Scheduling Terminology – simplified (cont.)
Resource Limited Schedule: A project schedule whose start and finish dates reflect expected resource availability.
Program Evaluation and Review Tool (PERT): An event and probability-based network analysis system generally used in projects where activities and their durations are difficult to define.

## Slide 12: Labels for Activity Nodes
ES | Earliest Start |  | DUR | Duration of Activity |  |  | 
EF | Earliest Finish |  | FLT | Float |  |  | 
LS | Latest Start |  |  |  |  |  | 
LF | Latest Finish |  |  |  |  |  | 

## Slide 13: Defining the numbers
1) Do the Forward Pass first to determine ES and EF
2) Do a Backwards Pass next to determine LF and LS
3) Subtract ES from LS to determine FLOAT

## Slide 14: Series/Parallel Activities
Series
Parallel

## Slide 15: Activities Merge / Burst
Merge
Burst

## Slide 16: Creating a Project Network Activity Diagram - Example

## Slide 17: Activity on Node Network

## Slide 18: Constructing the Critical Path

## Slide 19: Project Activity Network Showing Project Durations

## Slide 20: Rules when using the Forward Pass
Add all activity times along each path as we move through the network (ES + Duration = EF)
Carry the EF time to the activity nodes immediately ahead of the previous completed node. That EF becomes the ES of the next node, unless the next node is a merge point.
At a merge point, the largest previous EF becomes the ES for that node

## Slide 21: Activity Network with Forward Pass

## Slide 22: Rules when using the Backward Pass
Subtract activity times along each path as you move through the network (LF – Dur = LS)
Carry back the LS time to the activity nodes immediately before the next node. That LS becomes the LF of the previous node, unless the previous node is a burst point.
In the case of a burst point, the smallest following LS becomes the LF for that node.

## Slide 23: Activity Network with Backward Pass

## Slide 24: Completed Network Activity Diagram with Critical Path and Slack Times Calculated
Critical Path in bold
LS – ES or LF – EF = the Float. Activities that have a zero float cannot be delayed without delaying the entire project. These tasks together form the critical path.

## Slide 25: Network Activity Diagram example that Illustrates Laddering technique
If Tasks A1,B1 and C1 do not need the same resources then they could run simultaneously.

## Slide 26: Network Activity Diagram example that Illustrates Laddering technique
If Tasks A1, B1 and C1 need the same resources then they could run in a laddered start. That way once Task A1 was completed with the resource, Task B1 could then use it and then Task C1.

## Slide 27: Network Activity Diagram example that Illustrates Hammocking technique
Hammocking activities can be used as summaries for diagram segments of series activities. This allows for a smaller diagram that is less confusing.

## Slide 28: Steps to Reduce the Critical Path
Eliminate tasks on the Critical Path
Re-plan series paths to be parallel
Overlap sequential tasks
Shorten the duration on critical path activities
  Shorten earlier starting tasks
  Shorten longest tasks
  Shorten easiest tasks
  Shorten tasks that cost the least to speed up.

## Slide 29: Activity Duration Estimating
There are several methods:
Expert judgment estimating: Guided by historical information this can be used whenever possible.
Analogous estimating: A method of estimating that employs using a similar activity from a previous project as the basis for establishing the likely duration of a future schedule activity.
Parametric estimating: The quantity of work divided by the productivity rate. For example, total labor hours divided by man hours per day, or cable installation in meters of cable divided by meters per hour.
Reserve analysis estimating: An output of risk analysis, it can be employed to add empty buffers in project timing to deal with risk as part of a contingency plan.
Three point Method: PERT (Program Evaluation Review Technique)

## Slide 30: Activity Duration Estimate – PERT Estimate

## Slide 31: Pert Example
Calculate the estimated time to complete each of the following tasks.

## Slide 32: Pert Example
Calculate the estimated time to complete each of the following tasks.
26.33
12.83
19
10
14.83

## Slide 33: AON Example 1
Activity | Predecessors | Duration (days)
A | None | 5
B | A | 8
C | B | 3
D | A | 4
E | C | 5
F | C | 7
G | D, E | 6
H | F | 8
I | G | 6
J | H, I | 5

## Slide 34: AON Example 1
Activity | Predecessors | Duration (days)
A | None | 5
B | A | 8
C | B | 3
D | A | 4
E | C | 5
F | C | 7
G | D, E | 6
H | F | 8
I | G | 6
J | H, I | 5

## Slide 35: AON Example 2
Activity | Predecessors | Duration (days)
A | None | 3
B | A | 4
C | A | 2
D | B | 5
E | C | 1
F | E | 2
G | D, E | 4
H | F, G | 3
I | H | 6