- The students must first be divided in groups (2-4), create a company and associated logo pertaining to their project at hand.

- Each group will have one Project Manager.

- Each phase (A, B and C) will have a different Project Manager.

- The Project Manager will submit the Group report containing the items in the following sections. However, this is a team effort, and all group members are expected to contribute. If one or more members do not contribute, then they will receive no marks for the group submission.

- Each Project Manager will submit a Project Manager report at the same time as the group project. A template is provided.

- Each Team Member who is not a project manager for the current phase will submit a Team Member report at the same time as the group project. A template is provided.

- All report submissions will be digital through FanshaweOnline (FOL)

- Upload a single PDF file containing the entire group submission along with the files in original format

(5 Marks)

The report should have a cover sheet and follow the provided template.

- All items should be easy to read and understand.

- Any diagram should be large enough to read the text on the diagram. Large diagrams may be broken into parts so long as it is easy to follow.

(5 Marks)

- The report should include (and start with) the Project Charter, Scope Statement and WBS

- Corrections should be made based on feedback from Phase A

|  | (20 Marks) |  |
| --- | --- | --- |
|  | AON Duration Table: 5 marks | A table with your activities, their durations, predecessors, and successors must be included |
|  |  | Durations should be reasonable |
|  | AON Duration Format: | Durations should include units (days) |
|  | 5 marks | Should match the included WBS |
|  |  | Should have a code for each task |
|  | AON Diagram: 5 marks | Complete diagram, although some hammocking is allowed |
|  |  | Include a legend showing what box is for ES, LS, etc. |
|  |  | A reasonable number of activities should be in parallel |
|  | AON Diagram Calculations: 5 marks | Forward pass and backwards pass must be completed and correct |
|  |  | Identify the critical path |

Impact

Probabili

|  | (20 Marks) |  |
| --- | --- | --- |
|  | Risk Identification: 5 marks | Identify at least eight risks (or whatever your tutorial instructor requested) |
|  |  | Each risk is classified as covered in the class lectures |
|  | Risk Format: | Each risk is given a low, medium, or high impact |
|  | 5 marks | Each risk is given a low, medium, or high probability |
|  |  | Each risk is given a code |
|  |  | Each risk is identified as green, yellow, or red level of exposure depending on its impact and probability |
|  | Risk Mitigation: 5 marks | Devise a mitigation strategy for each yellow and red level exposure risk |
|  |  | Categorize the strategy as one of the types given in the lecture |
|  | Risk Matrix: | Create a Risk Matrix |
|  | 5 marks | Label it properly |
|  |  | Include the code for each identified risk in the correct cell |
|  |  | You do not require a risk in every cell |
|  |  | Colour the matrix to match the implied organization exposure level of each risk (green, yellow, red) |

|  | (15 Marks) |  |
| --- | --- | --- |
|  | Gantt Chart: 5 marks | Create a simple Gantt chart in Excel. |
|  |  | Activities should match your WBS and AON |
|  |  | Leave activities at “0% Complete for Phase B” |
|  | Gantt Format: | The unit of time should be days |
|  | 5 marks | The dates can be real dates or start with “Week 1” |
|  |  | Include arrows to show relations between task |
|  |  | Corner-to-corner tasks can imply Finish-to-Start relations without an arrow |
|  |  | All relations can be Finish-to-Start |
|  |  | The relations between tasks should match your AON |
|  | Milestones: 5 marks | Identify the end of activities that match your Milestones on your Gantt Chart with a diamond 𝘘. (You can also add the planned Milestone dates as a different symbol like ◆.) |
|  |  | Include a paragraph comparing your expected milestones in your Charter to your milestone dates in your Gantt. They do not need to be the same! |